PROJECT SPRINT

Sprint 1: 12 Dec – 26 Dec 2025

Goal: Project Setup + Basic UI Skeleton

Kirtan:

- Setup React project structure

- Build layout framework (Navbar, Footer, Routing)

- Implement pages: Home, About, Login/Register (from wireframe pages 1–3)

Krishna:

- Setup Node.js + Express project

- Design MongoDB schema draft (Users, Skills, Posts, Chats, Credits, Events)

- Setup basic API structure

Jagdish:

- Integrate JWT Auth structure

- Setup CI pipeline (GitHub Actions)

- Setup shared component library (buttons, inputs)

Sprint 2: 27 Dec – 10 Jan 2026

Goal: User Registration + Onboarding Flow

This covers your onboarding screens (pages 3–6 in wireframe)

wireframe v3

Kirtan:

- Implement onboarding screens (Personal Info, Skill Profile, Preferences)

- Skill add/remove UI

Krishna:

- Create APIs: register, login, onboarding update, skill CRUD

- Save skill proficiency level

Jagdish:

- Integrate frontend + backend

- Add validations + toast notifications

Sprint 3: 11 Jan – 25 Jan 2026

Goal: User Feed + Social Interactions

Matches feed pages in wireframe (middle section)

wireframe v3

Kirtan:

- Implement feed layout

- Post creation modal + list UI

Krishna:

- API for posts, likes, comments, news feed

Jagdish:

- Implement infinite scroll + real-time updates with Socket.io

- Basic moderation logic

Sprint 4: 26 Jan – 9 Feb 2026

Goal: Skill Swap System

Wireframe section: Skill swap forms + request confirmation

wireframe v3

Kirtan:

- Build skill swap UI

- Create swap request form components

Krishna:

- API for swap requests, matching algorithm

- DB models: SwapHistory, PendingRequests

Jagdish:

- Integrate flow: send request → notification → accept/decline

- Setup push notifications

Sprint 5: 10 Feb – 24 Feb 2026

Goal: Credits System + Transactions

Wireframe pages: “My Credits”, “Buy Credits”, “Transaction history”

wireframe v3

Kirtan:

- UI for credit wallet, purchase UI, transaction list

- Credit card/UPI form UI

Krishna:

- Credits DB

- Credits APIs: add, deduct, purchase (mock gateway first)

Jagdish:

- Integrate Razorpay/Stripe

- Implement success screens

Sprint 6: 25 Feb – 11 Mar 2026

Goal: Mentor Marketplace & Profile Pages

Wireframe pages: mentor list, user profile, skill rating pages

wireframe v3

Kirtan:

- Build mentor listing UI (filters, sorting)

- Build user public profile page

Krishna:

- Create mentor APIs (rating, availability, filters)

- Create profile update APIs

Jagdish:

- Integrate ratings + reviews

- Add profile media uploads

Sprint 7: 12 Mar – 26 Mar 2026

Goal: Chats + Messaging

Wireframe section: Chat UI (entire right bottom cluster)

wireframe v3

Kirtan:

- UI for chat list + chat detail

- Video call schedule UI

Krishna:

- Socket.io chat APIs

- Message storage + read/unread logic

Jagdish:

- Real-time typing indicator

- Push notifications for new messages

Sprint 8: 27 Mar – 10 Apr 2026

Goal: Resources Library + Instant Help

Wireframe: Resource cards + Instant Help provider list

wireframe v3

Kirtan:

- Resource listing + detail UI

- Instant-help provider cards

Krishna:

- APIs for resources, instant help request, filtering

Jagdish:

- Integrate help request → provider → confirmation

- Add urgency-level workflow

Sprint 9: 11 Apr – 20 Apr 2026

Goal: Events + Roadmap + Quiz System

Wireframe: Events list, event registration flow, quiz pages, roadmaps (last section)

wireframe v3

Kirtan:

- Build events page UI + event detail

- Build quiz UI (timers, MCQs)

Krishna:

- APIs for events, registration, quiz, score tracking

- Roadmap storage and mapping

Jagdish:

- Generate PDFs for roadmap

- Integrate quiz scoring + progression

Sprint 10: 21 Apr – 30 Apr 2026

Goal: Final Integration, QA & Deployment

Kirtan:

- Fix UI issues across all flows

- Add micro-interactions

Krishna:

- Optimize DB queries, security, API cleanup

Jagdish:

- Full-system QA

- Load testing

- Deployment on AWS/GCP + CI/CD